## Sheet1
Project Title	Week 1					Week 2					Week 3					Week 4					Week 5					Week 6
	Apr 9-13					Apr 16-20					Apr 23-27					Apr 30-May 4					May 7-11					May 14-18
Creating the board
-Make the board itself in the GUI
-Subdivide portions of the display for latter usage
Make pieces
-Code piece individually
-Code piece dynamics
Place where pieces are held and timer
Finishing touches
In-class Project Days
Final project presentation

Note that you will have in-class time to work on your project on Fri 27 Apr, Fri 4 May, and Fri 11 May. Project presentations will be held on Wed 16 May.